## PM Completeion
Staff (initial) | Building - 300 |  | Building - 400 |  | Building - 500 |  | Building - 550 |  | Building - 600 |  | Building - 900 |  | Building - 1000 |  | Building - 2000 |  | Building - 3000 |  | Building - 4000 |  | Building - 5000 |  | Building - 6000 (F) |  | Building - A |  | Building - B |  | Building - C |  | Building - D |  | Building - E (100) |  | Building - E (200) |  | Building - Cortyard Café |  | Building - Firing Range | Ponding basin | Containers
| PM | PM-AC | PM | PM-AC | PM | PM-AC | PM | PM-AC | PM | PM-AC | PM | PM-AC | PM | PM-AC | PM | PM-AC | PM | PM-AC | PM | PM-AC | PM | PM-AC | PM | PM-AC | PM | PM-AC | PM | PM-AC | PM | PM-AC | PM | PM-AC | PM | PM-AC | PM | PM-AC | PM | PM-AC | PM | PM | PM | PM-AC
CM | [7 empty] | NA |  |  |  | 2018-04-24
JR | 2017-04-24 |  | 2017-04-27 |  | 2019-04-10 |  | 2019-06-06 | NA | 2019-06-07 | [5 empty] | 2020-10-29 |  | 2020-01-24 |  | 2020-01-24 |  | 2020-01-24 |  | 2021-02-11 |  | 2019-11-04 |  | 2016-12-12 |  | 2018-01-23 |  | 2018-03-28 |  |  |  | 2017-10-02 |  | 2016-10-06 |  | 2018-11-01
| ** | ** | 2021-02-16 |  | 2021-02-18 |  |  |  | 2021-02-23 |  | 2021-03-09 |  | 2020-07-17 |  | 2020-10-29 |  | 2020-11-16 |  | 2020-11-30 |  | 2021-01-08 |  | 2021-03-02 |  |  |  | **** | **** |  |  | 2020-03-11 |  | * | * |  |  |  |  | 2020-03-06 | 2020-03-06 | 2020-03-06
* | BLDG 100 renovation completed
** | BLDG 300 currently under renovation
**** | BLDG B was slated for renovation but has been postponed
PM Total areas | 21 areas | 14 completed | 8 pending | 76.19%
AC Total areas | 20 areas | 0 completed | 20 pending | 0%
NOTE:
After COVID19 lockdowns, guidenace given was to "skip" or " not to play catch up" with the buildings that were missed due to the COVID19 lockdown

## PM Schedule
BUILDING | Schuled PM&I | PM&I Work Days | Total days | Month | BLDG # | PM&I Work Days | Total days | Month | BLDG # | PM&I Work Days | Total days
1000 | Monday , July 6, 2020 | 6 | 9 | 1st week OCT | E100 | 3 | 4 | 1st week OCT | E100 | 3 | 4
2000 | Monday , July 20, 2020 | 5 | 9 | 2nd Week OCT | E200 | 3 | 4 | 2nd Week OCT | E200 | 3 | 4
3000 | Thurdsay, July 23, 2020 | 6 | 9 | 3rd Week OCT | GCC Diner | 1 | 1 | 3rd Week OCT | GCC Diner | 1 | 1
4000 | Wedensday, August 5, 20220 | 3 | 5 | 3rd Week OCT | Firing Range | 1 | 1 | 3rd Week OCT | Firing Range | 1 | 1
5000 | Wednesday, August 5, 2020 | 7 | 10 | 4th Week OCT | Containers | 1 | 1 | 4th Week OCT | Containers | 1 | 1
6000 | Friday, August 21, 2020 | 7 | 10 | 4th WeekOCT | Ponding Basins | 1 | 1 | 4th WeekOCT | Ponding Basins | 1 | 1
300 | Under Construction |  | 3 | 1st/2nd week NOV | 1000 | 6 | 9 | 1st/2nd week NOV | 1000 | 6 | 9
400 | Wednesday, September 2, 2020 | 2 | 3 | 3rd / 4th week NOV | 2000 | 5 | 9 |  | 2000 | 5 | 9
500 | Thursday, Septemeber 10, 2020 | 2 | 3 | 1st/2nd week DEC | 3000 | 6 | 9 | 1st/2nd week DEC | 3000 | 6 | 9
600 | Monday, Spetmeber 14, 2020 | 2 | 3 | 3rd week of DEC | 4000 | 3 | 5 | 3rd week of DEC | 4000 | 3 | 5
900 | Friday, Spetemeber18, 2020 | 2 | 3 | 1st/2nd week JAN | 5000 | 7 | 10 | 1st/2nd week JAN | 5000 | 7 | 10
A | Tuesday, Septemeber 22, 2020 | 2 | 3 | 3rd/4th Week JAN | 6000 | 7 | 10 | 3rd/4th Week JAN | 6000 | 7 | 10
B | Wednesday, September 23, 2020 | 1 | 1 | 1st week FEB | 400 | 2 | 3 | 1st week FEB | 400 | 2 | 3
C | Friday, Spetemeber 25, 2020 | 2 | 3 | 1st/2nd week FEB | 500 | 2 | 3 | 1st/2nd week FEB | 500 | 2 | 3
D | Tueday, Septemeber 18, 2020 | 2 | 3 | 2nd/3rd week FEB | 600 | 2 | 3 | 2nd/3rd week FEB | 600 | 2 | 3
E -100 | Friday, October 2, 2020 | 3 | 4 | 3rd/4th week FEB | 900 | 2 | 3 | 3rd/4th week FEB | 900 | 2 | 3
E -200 | Wednesday, October 7 , 2020 | 3 | 4 | 4th week FEB | A | 2 | 3 | 4th week FEB | A | 2 | 3
GCC Diner | Monday, October 12, 2020 | 1 | 1 | 1st week MAR | B | 1 | 1 | 1st week MAR | B | 1 | 1
Firing Range | Wednesday, October 5, 2020 | 1 | 3 | 1st Week MAR | C | 2 | 3 | 1st Week MAR | C | 2 | 3
Conatiners | Thursday, October 15, 2020 | 1 | 3 | 2nd week MAR | D | 2 | 3 | 2nd week MAR | D | 2 | 3
Ponding Basins | Friday, October 16, 2020 | 1 | 2 | Anticiapted | 300 | Future | Future | 3rd week MAR | 550 | 1 | 2
Anticiapted | Forensics | Future | Future | Anticiapted | Forensics | Future | Future | Anticiapted | 300 | Future | Future
Anticiapted | Health & Wellness | Future | Future | PM schedule |  |  | AS of 8NOV19 | Anticiapted | Forensics | Future | Future
PM schedule |  |  | AS of 4NOV19 |  |  |  |  | Anticiapted | Health & Wellness | Future | Future
[8 empty] | PM schedule |  |  | As of 8JAN21